## Sheet1
TASKS | Start Date | Completion Date | Number of Days | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24
Project Selection and Drafting of Proposald-D1
Choosing the project idea. | 2023-10-10 | 2023-10-15 | 5 | bar: Week 1
Conducting preliminary research and drafting the project proposal. | 2023-10-15 | 2023-10-21 | 6 | bar: Week 2
Supervisor Meeting for Proposal Approval | 2023-10-21 | 2023-10-22 | 1 | bar: Week 2
Presenting the proposal to the supervisor and getting approval. -M1 | 2023-10-22 | 2023-10-22 | 0 | bar: Week 2
Project Kick-Off and Initial Planning
Finalizing the project scope and objectives post-approval-D2 | 2023-10-22 | 2023-10-30 | 8 | bar: Week 3
Outlining the detailed plan and schedule for the project. | 2023-10-30 | 2023-10-30 | 0 | bar: Week 3
Research on Machine Vision Algorithms | 2023-10-30
Initiating research on machine vision for species recognition- D3 | 2023-10-30 | 2023-11-27 | 28 | bar: Week 4 to Week 6
Supervisor meeting to discuss research direction and findings. | 2023-11-27 | 2023-11-27 | 0 | bar: Week 6
Starting Development of Health Assessment Algorithms-D4 | 2023-11-27
Beginning research and development on health assessment algorithms. | 2023-11-27 | 2023-12-25 | 28 | bar: Week 7 to Week 10
Health-Optimized Nutritional Dispensing Research-D5 | 2023-12-25
Supervisor meeting to discuss nutritional requirements and algorithm design. | 2023-12-25 | 2023-12-25 | 0 | bar: Week 10
Further research into nutritional needs and dietary management. | 2023-12-25 | 2024-01-08 | 14 | bar: Week 11
Development of the Prototype | 2024-01-08
Building the initial prototype of the feeding system. | 2024-01-08 | 2024-01-29 | 21 | bar: Week 12 to Week 14
Supervisor meeting for prototype review and feedback. | 2024-01-29 | 2024-01-29 | 0 | bar: Week 15
Enhancing Algorithm Accuracy | 2024-01-29
Improving machine vision and health assessment algorithms. | 2024-01-29 | 2024-02-12 | 14 | bar: Week 16 to Week 17
System Integration-M2 | 2024-02-12
Beginning the integration of different components (vision system, health assessment, and feeder). | 2024-02-12 | 2024-03-04 | 21 | bar: Week 16 to Week 18
Preparing for System Testing-D9 | 2024-03-04 | 2024-03-04
Setting up testing environments and protocols. | 2024-03-04 | 2024-03-11 | 7 | bar: Week 19
Comprehensive Testing and Validation | 2024-03-11
Conducting extensive tests of the integrated system. | 2024-03-11 | 2024-03-18 | 7 | bar: Week 20
Supervisor meeting to discuss initial testing results. | 2024-03-18 | 2024-03-25 | 7 | bar: Week 21
Final Adjustments and Completion-D9 | 2024-03-25
Finalizing the system and preparing for project presentation.-M4 | 2024-03-25 | 2024-04-01 | 7 | bar: Week 22
Supervisor meeting for final review and approval. | 2024-04-01 | 2024-04-08 | 7 | bar: Week 23
Documentation and Presentation Preparation | 2024-04-08
Compiling project documentation and preparing for the final presentation.-D10 | 2023-10-10 | 2024-04-15 | 188
KEYS
Milestones