## Sheet1
VFH
[5 empty] | Numbe Of Days in the Week | 7
Tasks | Start Date | Weeks Need | Days Needed | Completion Date
Project Selection and Drafting of Proposal
Choosing the project idea. | 2023-10-10 | 0.71429 | 5 | 2023-10-15
Conducting preliminary research and drafting the project proposal. | 2023-10-15 | 0.85714 | 6 | 2023-10-21
Supervisor Meeting for Proposal Approval | 2023-10-21 | 0.14286 | 1 | 2023-10-22
Presenting the proposal to the supervisor and getting approval. | 2023-10-22 |  | 0 | 2023-10-22
| 2023-10-22 |  | 0 | 2023-10-22
| 2023-10-22 |  | 0 | 2023-10-22
Project Kick-Off and Initial Planning | 2023-10-22 |  | 0 | 2023-10-22
Finalizing the project scope and objectives post-approval. | 2023-10-22 | 1.1429 | 8 | 2023-10-30
Outlining the detailed plan and schedule for the project. | 2023-10-30 |  | 0 | 2023-10-30
| 2023-10-30 |  | 0 | 2023-10-30
Research on Machine Vision Algorithms | 2023-10-30 |  | 0 | 2023-10-30
Initiating research on machine vision for species recognition. | 2023-10-30 | 4 | 28 | 2023-11-27
Supervisor meeting to discuss research direction and findings. | 2023-11-27 |  | 0 | 2023-11-27
| 2023-11-27 |  | 0 | 2023-11-27
Starting Development of Health Assessment Algorithms | 2023-11-27 |  | 0 | 2023-11-27
Beginning research and development on health assessment algorithms. | 2023-11-27 | 4 | 28 | 2023-12-25
| 2023-12-25 |  | 0 | 2023-12-25
| 2023-12-25 |  | 0 | 2023-12-25
Health-Optimized Nutritional Dispensing Research | 2023-12-25 |  | 0 | 2023-12-25
Supervisor meeting to discuss nutritional requirements and algorithm design. | 2023-12-25 |  | 0 | 2023-12-25
Further research into nutritional needs and dietary management. | 2023-12-25 | 2 | 14 | 2024-01-08
| 2024-01-08 |  | 0 | 2024-01-08
| 2024-01-08 |  | 0 | 2024-01-08
Development of the Prototype | 2024-01-08 |  | 0 | 2024-01-08
Building the initial prototype of the feeding system. | 2024-01-08 | 3 | 21 | 2024-01-29
Supervisor meeting for prototype review and feedback. | 2024-01-29 |  | 0 | 2024-01-29
| 2024-01-29 |  | 0 | 2024-01-29
Enhancing Algorithm Accuracy | 2024-01-29 |  | 0 | 2024-01-29
Improving machine vision and health assessment algorithms. | 2024-01-29 | 2 | 14 | 2024-02-12
| 2024-02-12 |  | 0 | 2024-02-12
| 2024-02-12 |  | 0 | 2024-02-12
System Integration | 2024-02-12 |  | 0 | 2024-02-12
Beginning the integration of different components (vision system, health assessment, and feeder). | 2024-02-12 | 3 | 21 | 2024-03-04
| 2024-03-04 |  | 0 | 2024-03-04
| 2024-03-04 |  | 0 | 2024-03-04
Preparing for System Testing | 2024-03-04 |  | 0 | 2024-03-04
Setting up testing environments and protocols. | 2024-03-04 | 1 | 7 | 2024-03-11
| 2024-03-11 |  | 0 | 2024-03-11
Comprehensive Testing and Validation | 2024-03-11 |  | 0 | 2024-03-11
Conducting extensive tests of the integrated system. | 2024-03-11 | 1 | 7 | 2024-03-18
Supervisor meeting to discuss initial testing results. | 2024-03-18 | 1 | 7 | 2024-03-25
| 2024-03-25 |  | 0 | 2024-03-25
Final Adjustments and Completion | 2024-03-25 |  | 0 | 2024-03-25
Finalizing the system and preparing for project presentation. | 2024-03-25 | 1 | 7 | 2024-04-01
Supervisor meeting for final review and approval. | 2024-04-01 | 1 | 7 | 2024-04-08
| 2024-04-08 |  | 0 | 2024-04-08
Documentation and Presentation Preparation | 2024-04-08 |  | 0 | 2024-04-08
Compiling project documentation and preparing for the final presentation. | 2024-04-08 | 1 | 7 | 2024-04-15
Formulas:
Completion Date = +[Days Needed]+[Start Date]
Start Date = +[Completion Date, row above]